## Sheet1
Schedule for Smarthome lighting/fan controls via Zigbee
525.743 Embedded Systems Development Lab, Fall 2015
week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
date | 20150831 | 20150907 | 20150914 | 20150921 | 20150928 | 20151005 | 20151012 | 20151019 | 20151026 | 20151102 | 20151109 | 20151116 | 20151123 | 20151130 | 20151207 | 20151214
First class - initial ideas
Second class - review ideas and commit
PDR
CDR (Critical Design Review)
Software tools isntall
Arduino Zigbee communication
Arduino SD card data access
Arduino LCD touch sensing
Arduino LCD graphics
Server Zigbee
Server event logging
Server vacation mode events
Server LCD panel
Server LCD touch
Arduino triac interface for lights/fans
Android connection to server/status/logs
Android manual events to server
Android geofence events to server
Android NFC events to server
Demo
item | $ each | quantity | already | need | total
Arduino Uno |  | 7 | 3 | 4 | 0
Arduino Due |  | 7 | 1 | 6 | 0
Xbee/SD shield |  | 7 |  | 7 | 0
Xbee module |  | 8 |  | 8 | 0
LCD/touch/SD shield |  | 4 |  | 4 | 0
triac |  |  |  | 0 | 0
AMD Gizmo (Linux server) |  | 1 | 1 | 0 | 0
PCIe x1 slot connector (server/Xbee) |  | 1 |  | 1 | 0
touch LCD 7" (server) |  | 1 | 1 | 0 | 0
Android with GPS/NFC |  | 1 | 1 | 0 | 0
Android with GPS, no NFC |  | 1 | 1 | 0 | 0
small breadboard |  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
total |  |  |  |  | 0